## SMC-App
Functional Certification Plan
Project name: |  | SmartConsent |  | Module: | App
Prepared by: |  | Sandra Duque |  | Validated by: | Sandra Duque
Test # | Option | Functionality | Date | Date Used | Test Manager | Test Results | Approved (YES / NO) | Responsible
1 | New Smart Consent | Generate signed informed consent (PDF) in Health Center | 2021-06-16 | Mobile App User: RAMOSJ Password: 4915 | Sandra Duque | a) Presents list of specialties (b) Presents a list of procedures c) Presents list of patients d) Presents PERSONAL DATA PROTECTION screen e) Presents GENERAL DATA screen f) Presents consent screen document (g) Submit screen PROCEDURE VIDEO h) Presents RECORD screen i) PATIENT SIGNATURE SPECIALIST FIRM VIEW PDF y RETURN HOME | YES | Sandra Duque
2 | New Smart Consent - Home Sign | Generate Signed Informed Consent (PDF) | 2021-06-16 | Mobile App User: RAMOSJ Password: 4915 | Sandra Duque | Pending visualization of all patients | NO | Sandra Duque
3 | Login and profile by role / Segregation of duties | Present options according to roles: specialist | 2021-06-16 | Mobile App | Sandra Duque | Segregation of duties by user Specialist: Functions: Create/Visualize Patients Create /Display consents | YES | Sandra Duque

## SMC-Web
Functional Certification Plan
Project name: |  | SmartConsent |  | Module: | App
Prepared by: |  | Sandra Duque |  | Validated by: | Sandra Duque
Test # | Option | Functionality | Date | Date Used | Test Manager | Test Results | Approved (YES / NO) | Responsible
1 | User access | Access is made with a username and password | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | The system was accessed and the administrative panel screen is presented correctly and in English language | YES | Sandra Duque
2 | User access | Access is made with a wrong username and password | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 101010 | Sandra Duque | The invalid user or password alert message is generated, correct spelling of the word: valid is required. | YES/NO Pending spelling | Sandra Duque
3 | User access | Access is made with an empty username and password | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: vacio Password: vacio | Sandra Duque | a) There is no validation in the User and Password fields. b) Does not generate alert message, it is required to present message to type username and password | NO | Sandra Duque
4 | Validation Misspellings | Validate Texts and Misspellings in: (a) Home page/Homepage of the Administrative Panel b) Administrations --> Catalogs--> Create | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) It is necessary to correct to singular the word diagnosis and the word urgencies, start with lowercase. b) Correct spelling word Catalogs | NO | Sandra Duque
5 | Administrations --> Catalogs--> List | Allows you to view catalog of specialties | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | List of catalogues is presented correctly. Catalogues: countries gender roles specialties, among others | YES | Sandra Duque
6 | Administrations --> Catalogs--> Specialties | Allows you to create specialties and procedures in catalogs | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) There is no validation in the fields b) issue was detected when creating empty procedure for a specialty. | NO | Sandra Duque
7 | Administrations à Proc. Estab (Views) | Select: 1) Establishment 2) Specialties 3) Procedures by Specialties | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) At the time of selecting the Establishment, then Specialty, the associated procedures are presented, however, it happens that the information of the name of the Establishment and Specialty is hidden. b) It is suggested to review the presentation of the fields in this flow. c) A Back or Back or Cancel button is required to navigate the view | NO | Sandra Duque
8 | Administrations à Establishment | Allows you to add Establishment | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | Allows you to add an Establishment correctly. remarks a) In the detail view of the Establishment menu, it is proposed to hide the field: Url Hash. b) Add Catalog Type, related to Establishment | YES with observations | Sandra Duque
9 | Administrations à Establishment (Consult) | Querying Establishment data | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) In the detail view of the Establishment, the fields Address, E-mail, Phone, Contact name, Contact phone are presented encrypted. b) It is required to present legible the aforementioned fields. | NO | Sandra Duque
10 | Administrations à Patients | Allows you to add Patients | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | By clicking the NEW button, the fields have been completed and the patient was successfully generated | YES | Sandra Duque
11 | Administrations à Patients | Seeing the Patients view | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) In the general view of the Patients menu, the fields are presented encrypted: medical history number, DNI, Name and surname, date of birth, address, E-mail, the picture field is presented as numerical. b) It is required to decrypt the aforementioned fields and present in a legible form. | NO | Sandra Duque
12 | All modules (Navigability between screens) | All modules | 2021-06-04 | url: http://forms.e-processmed.com:4100/login User: "Doctor 1" Password: 12345 | Sandra Duque | a) In each module/submodule and views, add the navigability buttons such as return and/or cancel, considering the functionality. b) Consider in the cascade type menus, keep the information visible in each iteration. c) Consider the responsive technique in the design of the screens of the EPM solution d) In the views, position the Save and/or Ok and/or Cancel buttons at the top with the objective that is kept visible. e) Correct spelling on homepage page and all views. | NO | Sandra Duque
| Latency in site loading | Sites: url: http://forms.e-processmed.com:4100/login url: http://forms.e-processmed.com:4100/consent | 2021-06-10 | Sitios: url: http://forms.e-processmed.com:4100/login url: http://forms.e-processmed.com:4100/consent | Sandra Duque | In browsers Safari, Google Chrome, Internet Explorer, there is a delay in loading sites | NO | Sandra Duque
| Login and profile by role / Segregation of duties | Present options according to roles: specialist administrator | 2021-06-16 | https://ledger.e-processmed.com/login | Sandra Duque | Options that the Establishment Administrator user must have: Functions: (a) To amend establishment details b) Select Specialties/Procedures/videos c) Create users and roles | NO | Sandra Duque
| Login and profile by role / Segregation of duties | Present options according to roles: specialist administrator | 2021-06-16 | https://ledger.e-processmed.com/login | Sandra Duque | Options that the Specialist user must have: Functions: Create/Visualize Patients View consents | YES | Sandra Duque